## Sheet1
Project Name | SudMig
Project Manager | Stamatina Tounta
Project Deliverable | SudMig Dashboard
Start Date | 2023-10-03
End Date | 2024-01-31
Overall Progress | 20%
Tasks | Responsible | Start | End | Days | Status | 2023-10-03 | 2023-10-10 | 2023-10-17 | 2023-10-24 | 2023-10-31 | 2023-11-07 | 2023-11-14 | 2023-11-21 | 2023-11-28 | 2023-12-05 | 2023-12-12 | 2023-12-19 | 2023-12-26 | 2024-01-02 | 2024-01-09 | 2024-01-16 | 2024-01-23 | 2024-01-30
Project Management | [6 empty] | Start | [15 empty] | End
"Project overview" maintenance | Noah | 2023-10-10 | 2024-01-31 | 113 | In progress
GitLab maintenance | Matina | 2023-10-11 | 2024-01-31 | 112 | In progress
Topic and Data | [6 empty] | Start |  |  |  |  | End
Set topic | Noah | 2023-10-10 | 2023-10-16 | 6 | Complete
Find data | Matina | 2023-10-10 | 2023-10-31 | 21 | Complete
Define stakeholders | Noah | 2023-10-31 | 2023-11-15 | 15 | Complete
Data Processing | [11 empty] | Start |  |  | End
Data pre-processing | Noah | 2023-11-11 | 2023-12-05 | 24 | In progress
Integration in DBMS | Matina | 2023-12-06 | 2023-12-10 | 4 | Not started
Services | [15 empty] | Start | End
Services definintion | Noah | 2023-12-11 | 2023-12-13 | 2 | Not started
Services creation | Matina | 2023-12-14 | 2023-12-18 | 4 | Not started
Communication | [16 empty] | Start |  |  |  | End
Decide on communication platform | Matina | 2023-12-21 | 2023-12-22 | 1 | Not started
Layout design | Noah | 2023-12-23 | 2023-12-30 | 7 | Not started
Metadata | Matina | 2023-12-15 | 2024-01-05 | 21 | Not started
Data integration | Matina | 2024-01-01 | 2024-01-15 | 14 | Not started
Documentation | [20 empty] | Start |  | End
Report compilation | Noah | 2024-01-16 | 2024-01-31 | 15 | Not started
Submission |  | 2023-01-31 | 2023-01-31