## Milestone plan
Milestones project SudMig
PROJECT DETAILS
| DATE | Milestone | POSITION | BASISPLAN | Angepasste Position | Angepasstes Datum | Angepasster Meilenstein
| 2023-10-03 | Project Start | 25 | 0 | 25 | 2023-10-03 | Project Start
| 2023-11-10 | Topic stakeholder identification | 10 | 0 | 10 | 2023-11-10 | Topic stakeholder identification
| 2023-11-15 | Data collection | -10 | 0 | -10 | 2023-11-15 | Data collection
| 2023-11-28 | Mid-term presentation | 25 | 0 | 25 | 2023-11-28 | Mid-term presentation
| 2023-12-03 | Submitted project overview document | -15 | 0 | -15 | 2023-12-03 | Submitted project overview document
| 2023-12-06 | Data preparation | 20 | 0 | 20 | 2023-12-06 | Data preparation
| 2023-12-10 | Integration of data in DB | -15 | 0 | -15 | 2023-12-10 | Integration of data in DB
| 2023-12-20 | Establish Web Service(s) | 20 | 0 | 20 | 2023-12-20 | Establish Web Service(s)
| 2023-12-30 | Design dashboard | 15 | 0 | -20 | 2024-01-23 | Final presentation
| 2024-01-05 | Describe and publish metadata | 25 | 0 | 25 | 2024-01-05 | Describe and publish metadata
| 2024-01-15 | Integration of data into dashboard | -15 | 0 | 15 | 2023-12-30 | Design dashboard
| 2024-01-23 | Final presentation | -20 | 0 | -20 | 2024-01-23 | Final presentation
| 2024-01-31 | Compile project report | 15 | 0 | 25 | 2024-01-05 | Describe and publish metadata
| 2024-01-31 | Project end | -25 | 0 | -15 | 2024-01-15 | Integration of data into dashboard

## Projektdaten sortiert (hidden)
Daten sortieren, um die Zeitachse in chronologischer Reihenfolge aufzufüllen
|  |  | Datenanalyse | [5 empty] | Reale im Diagramm abzubildende Daten, die über die verborgenen Spalten F–H in die Zeitachse gespeist werden.
| Anfangszeile | 6 | TIE BREAK | RANG | DATUM | MEILENSTEIN | POSITION | NUM | RANG sortiert | DATUM | MEILENSTEIN | POSITION
| letzter Eintrag | 19 | 14 | 1 | 2023-10-03 | Project Start | 25 | 13 | 14 | 2023-10-03 | Project Start | 25
|  |  | 13 | 2 | 2023-11-10 | Topic stakeholder identification | 10 | 12 | 13 | 2023-11-10 | Topic stakeholder identification | 10
|  |  | 12 | 3 | 2023-11-15 | Data collection | -10 | 11 | 12 | 2023-11-15 | Data collection | -10
|  |  | 11 | 4 | 2023-11-28 | Mid-term presentation | 25 | 10 | 11 | 2023-11-28 | Mid-term presentation | 25
|  |  | 10 | 5 | 2023-12-03 | Submitted project overview document | -15 | 9 | 10 | 2023-12-03 | Submitted project overview document | -15
|  |  | 9 | 6 | 2023-12-06 | Data preparation | 20 | 8 | 9 | 2023-12-06 | Data preparation | 20
|  |  | 8 | 7 | 2023-12-10 | Integration of data in DB | -15 | 7 | 8 | 2023-12-10 | Integration of data in DB | -15
|  |  | 7 | 8 | 2023-12-20 | Establish Web Service(s) | 20 | 6 | 7 | 2023-12-20 | Establish Web Service(s) | 20
|  |  | 6 | 9 | 2023-12-30 | Design dashboard | 15 | 5 | 6 | 2023-12-30 | Design dashboard | 15
|  |  | 5 | 10 | 2024-01-05 | Describe and publish metadata | 25 | 4 | 5 | 2024-01-05 | Describe and publish metadata | 25
|  |  | 4 | 11 | 2024-01-15 | Integration of data into dashboard | -15 | 3 | 4 | 2024-01-15 | Integration of data into dashboard | -15
|  |  | 3 | 12 | 2024-01-23 | Final presentation | -20 | 2 | 3 | 2024-01-23 | Final presentation | -20
|  |  | 1 | 13 | 2024-01-31 | Compile project report | 15 | 1 | 2 | 2024-01-31 | Project end | -25
|  |  | 2 | 13 | 2024-01-31 | Project end | -25 | 0 | 1 | 2024-01-31 | Compile project report | 15